## Work Breakdown Timeline
Financial Management System - Work Breakdown Timeline
Task | Start Date | End Date | Owner
Project Kickoff & Charter | 2025-03-17 | 2025-03-18 | Sonal Khobragade
Stakeholder Interviews & Register Setup | 2025-03-19 | 2025-03-21 | Sonal Khobragade
Draft BRD | 2025-03-22 | 2025-03-28 | Sonal Khobragade
BRD Review & Sign-off | 2025-03-29 | 2025-03-31 | Sonal Khobragade
Draft FRD & Data Models | 2025-04-01 | 2025-04-08 | Sonal Khobragade
UI Mockups & Wireframes | 2025-04-09 | 2025-04-12 | Sonal Khobragade
Develop Use Cases & Acceptance Criteria | 2025-04-13 | 2025-04-17 | Sonal Khobragade
Write User Stories & Prioritization | 2025-04-18 | 2025-04-21 | Sonal Khobragade
User-Story Mapping | 2025-04-22 | 2025-04-24 | Sonal Khobragade
Build Traceability Matrix | 2025-04-25 | 2025-04-27 | Sonal Khobragade
Draft Test Cases | 2025-04-28 | 2025-04-29 | Sonal Khobragade
Final Review & Handover | 2025-04-30 | 2025-04-30 | Sonal Khobragade